|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Task Mode | WBS | Task Name | Duration | Start | Finish | Predecessors | Resource Names |
| Auto Scheduled | 1 | Get new schedule | 5 mins | Wed 5/31/23 | Wed 5/31/23 |  |  |
| **Auto Scheduled** | **2** | **Word** | **20.99 days** | **Wed 5/31/23** | **Mon 9/4/23** |  |  |
| Auto Scheduled | 2.A | Read Word textbook and work through projects | 18 hrs | Wed 5/31/23 | Fri 6/9/23 | 1 | Kyle Smith,Aagam Shah |
| Auto Scheduled | 2.B | Review end-of-chapter exercises | 1 hr | Mon 9/4/23 | Mon 9/4/23 |  | Kyle Smith |
| Auto Scheduled | 2.C | Check all word | 1 hr | Mon 9/4/23 | Mon 9/4/23 |  | Kyle Smith |
| **Auto Scheduled** | **3** | **Excel** | **18.74 days** | **Fri 6/9/23** | **Mon 9/4/23** |  |  |
| Auto Scheduled | 3.A | Read Excel textbook and work through projects | 18 hrs | Fri 6/9/23 | Wed 6/21/23 | 3 | Kyle Smith,Aagam Shah |
| Auto Scheduled | 3.B | Review end-of-chapter exercises | 1 hr | Mon 9/4/23 | Mon 9/4/23 |  | Kyle Smith |
| Auto Scheduled | 3.C | Check all word | 1 hr | Mon 9/4/23 | Mon 9/4/23 |  | Kyle Smith |
| **Auto Scheduled** | **4** | **PowerPoint** | **16.49 days** | **Wed 6/21/23** | **Mon 9/4/23** |  |  |
| Auto Scheduled | 4.A | Read PowerPoint textbook and work through projects | 18 hrs | Wed 6/21/23 | Fri 6/30/23 | 7 | Kyle Smith,Aagam Shah |
| Auto Scheduled | 4.B | Review end-of-chapter exercises | 1 hr | Mon 9/4/23 | Mon 9/4/23 |  | Kyle Smith |
| Auto Scheduled | 4.C | Check all word | 1 hr | Mon 9/4/23 | Mon 9/4/23 |  | Kyle Smith |
| Auto Scheduled | 5 | Verify students and courses | 1 hr | Fri 6/30/23 | Fri 6/30/23 | 11 | William Cook |
| Auto Scheduled | 6 | Make necessary corrections to student list | 1 hr | Fri 6/30/23 | Mon 7/3/23 | 14 | William Cook |
| Auto Scheduled | 7 | Create labels with student name and course name | 2 hrs | Mon 7/3/23 | Mon 7/3/23 | 15 | William Cook |
| Auto Scheduled | 8 | Copy/print course materials | 3 hrs | Mon 7/3/23 | Wed 7/5/23 | 16 | Aagam Shah |
| Auto Scheduled | 9 | Set color-coded folders | 1 hr | Wed 7/5/23 | Wed 7/5/23 | 17 | John Walker |
| Auto Scheduled | 10 | Add labels and course materials to folders | 2 hrs | Wed 7/5/23 | Fri 7/7/23 | 18 | John Walker |
| Auto Scheduled | 11 | Get books from bookstore | 2 hrs | Fri 7/7/23 | Fri 7/7/23 | 19 | Aagam Shah |
| Auto Scheduled | 12 | Verify books and course material folders for each student | 2 hrs | Fri 7/7/23 | Mon 7/10/23 | 20 | David Grant |
| Auto Scheduled | 13 | Verify attendance sheets with books and course materials | 2 hrs | Mon 7/10/23 | Mon 7/10/23 | 21 | David Grant |
| Auto Scheduled | 14 | First Day | 0 days | Tue 9/5/23 | Tue 9/5/23 | 22 | Aagam Shah |