## Slide 1: PROJECT STATUS REPORT
Global Treps Project
PROJECT SPONSOR | SUE HAGEL
PERIOD COVERED | 6 Months
PROJECT CODE | MGMT866 GROUP 2 P3
PROJECT START DATE | 11/15/2023
PROJECT DUE DATE | 11/29/2023

## Slide 2
Agenda
Project Status Report
01
Project Alignment & Sponsor Approval
02
Communication Management Plan
03
Risk Register
04
Conclusion
05
Further Steps
06

## Slide 3: PROJECT STATUS REPORT
COMPONENT | STATUS | MEMBER / TEAM | NOTES
Team Charter and Pledge Form | COMPLETED | Subin Varughese | As a team we pledge to work together, communicate openly, and respect each other’s differences.
RACI Matrix | COMPLETED | Deepthi Muraleedharan & Subin Varughese | Waiting for the sponsor approval
Communication Management Plan | COMPLETED | Deepthi Muraleedharan & Subin Varughese | Waiting for the sponsor approval
Risk Register | COMPLETED | Chetna Chander & Agam Shah | Waiting for the sponsor approval
Probability/Impact Matrix | COMPLETED | Chetna Chander & Agam Shah | Waiting for the sponsor approval
Meeting Minutes | UP-TO-DATE | Subin Varughese | Keep updated through meetings throughout the duration of the project for deliverables status.
Power Point Slide Deck | IN PROGRESS | Team | Waiting for the sponsor approval
Team Responsibility and Tracking Worksheet | COMPLETED | Team | Waiting for the completion of deliverables
OVERALL PROJECT STATUS | 
ON TRACK

## Slide 4: Risk Register
No. | Risk | Triggers | Risk Owner | Impact
1 | Early Completion | Accelerated progress, effective task management | Team | High
2 | Technological Advancement | Adoption of new tools and techniques | Team | Medium
3 | Strategic Partnership | Partnership agreements, joint ventures | Project Manager | Low
4 | Budget Overrun | Changes in scope and additional resource expenditure | Project Director | High
5 | Staff Turnover | Dissatisfaction at work and outside employment opportunities | Project Director | Low
6 | Market competition | Price wars, loss of market share ,Poor consumer feedback and low demand. | Marketing Department | Medium

## Slide 5: Communication Management Plan
Stakeholders | Communications Name | Delivery Method/Format | Producer | Due/ Frequency
Injured Employee -Ashok | Sympathy and Recovery Wishes | Instant Messaging/Email | Subin Varughese | Monday, 10 am
Entire Team - Update | Team Update Email | Email | Subin Varughese | Every Tuesday, 8 pm
Entire Team - Announcement | Project Announcement | Virtual Team Meeting | Subin Varughese | Every Saturday, 12 pm
External Stakeholders | Weekly Status Report | Stakeholder Notification | All Team Members | Tuesday afternoon, 2 pm

## Slide 6: Conclusion
A project status report is an overview of the work that has been done and the successes that have been achieved during each stage.
The project alignment and sponsor approval paved the way for a strong execution phase with strategic accuracy, strong team collaboration, and a shared focus on project success.
The Change Control flowchart, we created a step-by-step process for change control, including key decision points and change management roles.
THE RISK REGISTER AND COMMUNICATION MANAGEMENT PLAN GUIDES US THROUGH THE COMPLEXITY OF THE PROJECT APPROVED BY THE SPONSOR.

## Slide 7: Further Steps
Develop a detailed project plan.
Budget approval from Sponsor to move to execution
Stakeholder Management and procurement
Meetings will be conducted to identify the risks, challenges, and resource management regarding the next phase.

## Slide 8
Thank You